## Sheet1
MSc Dissertation
Project Start: | 2024-09-16
Display Week: | 18 |  | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10
| Today | 2025-02-06 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16
TASK | START | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Semester 1 - Project Initiation and Planning | 2024-10-14 | 2024-10-21
Project Initiation and Planning | 2024-10-14 | 2024-10-20
Conduct Preliminary Literature Searches to identify potential topics | 2024-10-14 | 2024-10-20
Discuss ideas with Supervisor | 2024-10-14 | 2024-10-20
Set up Workspace | 2024-10-14 | 2024-10-20
Set up Obsidian Workspace | 2024-10-14 | 2024-10-20
Organise folders and notes for project management | 2024-10-14 | 2024-10-20
Make enquiries about own research | 2024-10-21 | 2024-10-27
Contact Employer about using their data for own research | 2024-10-21 | 2024-10-27
Contact Prof Elaine Cole regarding ethics of accessing non-NHS data | 2024-10-21 | 2024-10-27
Bounce Ideas off of supervisor | 2024-10-21 | 2024-10-27
Finalise Topic Selection | 2024-10-23 | 2024-11-10
Decide on specific focus for systematic review | 2024-11-10 | 2024-11-11
Develop Research Question and Objectives | 2024-11-11 | 2024-11-12
Use PICO framework | 2024-11-11 | 2024-11-12
Being drafting introduction | 2024-11-11 | 2024-11-12
Define Inclusion and Exclusion Criteria | 2024-11-11 | 2024-11-12
Design Search Strategy | 2024-11-12 | 2024-11-17
Identify databases and key search terms | 2024-11-12 | 2024-11-17
Test Initial Searches on key databases | 2024-11-12 | 2024-11-17
Draft Methodolgy Section | 2024-11-12 | 2024-11-17
Detail search strategy, study selection process and data extraction plan. | 2024-11-12 | 2024-11-17
Detail Timeline | 2024-11-12 | 2024-11-17
Create Timeline and Gantt Chart | 2024-11-12 | 2024-11-17
Use Microsoft Excel to create Gantt chart. | 2024-11-12 | 2024-11-17
Review and Revise Project Plan | 2024-11-18 | 2024-11-24
Incorporate Supervisor Feedback | 2024-11-18 | 2024-11-24
Proofread for clarity and coherence. | 2024-11-18 | 2024-11-24
Protocol Registration | 2024-11-25 | 2024-12-01
Register Protocol | 2024-11-25 | 2024-12-01
Consider registering with PROSPERO | 2024-11-25 | 2024-12-01
Pilot Search Strategy | 2024-12-09 | 2024-12-15
Run test searches in a few databases | 2024-12-09 | 2024-12-15
Adjust terms as necessary | 2024-12-09 | 2024-12-15
Full Literature Search | 2024-12-16 | 2024-12-22
Finalise Search Strategy | 2024-12-16 | 2024-12-22
Create a plan for screening and managing data | 2024-12-16 | 2024-12-22
Begin full literature search | 2025-01-02 | 2025-01-08
Start with primary databases | 2025-01-02 | 2025-01-08
Continue Literature Search | 2025-01-09 | 2024-01-15
Complete searches in all planned databases | 2025-01-09 | 2024-01-15
Save and organise search results | 2025-01-09 | 2024-01-15
Prepare for screening | 2025-01-16 | 2025-01-21
Remove duplicates in VS code using python | 2025-01-16 | 2025-01-21
Import unique papers to Zotero | 2025-01-16 | 2025-01-21
Semester 2 - Data Collection and Analysis | 2025-01-02 | 2025-04-17
Title and Abstract Screening | 2025-01-22 | 2024-02-18
Import unique papers to ASReview | 2025-01-22 | 2025-01-28
Begin title and abstract screening | 2025-01-22 | 2025-01-28
Apply inclusion/exclusion criteria | 2025-01-22 | 2025-01-28
Complete Title and Abstract Screening | 2025-01-29 | 2025-02-18
Resolve Uncertainties | 2025-01-29 | 2025-02-18
Document reasons for exclusions | 2025-01-29 | 2025-02-18
Full Text Screening | 2025-02-19 | 2025-03-11
Obtain full text articles | 2025-02-19 | 2025-03-11
Apply criteria fully | 2025-02-19 | 2025-03-11
Resolve Descrepancies | 2025-03-12 | 2025-03-18
Discuss with supervisor | 2025-03-12 | 2025-03-18
Finalise list of studies to include | 2025-03-12 | 2025-03-18
Update PRISMA flow diagram | 2025-03-19 | 2025-03-25
Data Extraction | 2025-03-26 | 2025-04-01
Begin Data Extraction | 2025-03-26 | 2025-04-15
Use prepared data extraction form in microsoft excel | 2025-03-26 | 2025-04-15
Quality Assessment | 2025-04-16 | 2025-04-17
Assess risk of bias | 2025-04-16 | 2025-04-17
Semester 3 - Data Synthesis and Writing | 2025-04-22 | 2025-07-06
Assess Heterogeneity | 2025-04-22 | 2025-04-28
Determine if meta-analysis is feasible | 2025-04-22 | 2025-04-28
Data Synthesis and Analysis | 2025-04-29 | 2025-05-05
Quantitative Analysis or narrative synthesis | 2025-04-29 | 2025-05-05
Conduct Meta-Analysis (if applicable) | 2025-05-06 | 2025-05-19
Develop narratie synthesis | 2025-05-06 | 2025-05-19
Identify themes and patterns | 2025-05-06 | 2025-05-19
Draft SPP Paper | 2025-05-20 | 2025-06-02
Introduction | 2025-05-20 | 2025-06-02
Methods | 2025-05-20 | 2025-06-02
Results | 2025-05-20 | 2025-06-02
Discussion | 2025-05-20 | 2025-06-02
Draft SPP Supplement | 2025-06-03 | 2025-06-16
Include supplementary analyses and additional tables | 2025-06-03 | 2025-06-16
Review and Revise Drafts | 2025-06-17 | 2025-06-23
Incorporate Supervisor Feedback | 2025-06-17 | 2025-06-23
Proofread and edit | 2025-06-17 | 2025-06-23
Prepare SPP Oral Presentation | 2025-06-24 | 2025-07-06
Develop slides for 20 minute presentation | 2025-06-24 | 2025-06-30
Record presentation | 2025-07-01 | 2025-07-06
Finalise all documents | 2025-07-01 | 2025-07-06
Check formatting and submission guidelines | 2025-07-01 | 2025-07-06

## Deadlines
Deadline | Date
Submit Topic Proposal | 2024-10-06
Submit Project Plan | 2024-11-24
SPP Components | 2025-07-06

## Holidays
Holiday | Start Date | End Date
Christmas Holiday | 2024-12-24 | 2024-12-27
New Years Holiday | 2024-12-30 | 2025-01-01